## hours
Date | Start time | Stop time | Spend time | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Catagorie
2025-06-26 | 10:00 | 13:00 | 3:00 | Tested power gpio expander & ADC. Expender can read en write. ADC is not operating. |  |  |  |  | hardware
2025-06-27 | 10:00 | 15:00 | 5:00 | Reasearched the SPI hardware of the ESP32 | Used the SPI hardware with display in test |  |  |  | software
2025-06-28 | 13:00 | 16:00 | 3:00 | Implemented hardware SPI in main software | Atempted to run main UI |  |  |  | software
2025-07-01 | 13:00 | 18:00 | 5:00 | Figuring out why display wont work | Updated pinout.xslx of all models |  |  |  | software
2025-07-04 | 10:30 | 16:00 | 5:30 | Fixed main display (missing code) |  |  |  |  | software
2025-07-05 | 9:00 | 16:00 | 7:00 | Started rebuilding UI in EEZ studio |  |  |  |  | software
2025-07-06 | 10:30 | 14:00 | 3:30 | Finishing UI basics in EEZ studion | Started designing code architecture |  |  |  | software
2025-07-07 | 10:00 | 15:00 | 5:00 | Setting up new project & freertos in vsc | Set up UI & display is working in VSC |  |  |  | software
2025-07-08 | 9:00 | 12:00 | 3:00 | Retreiving current time via wifi hotspot |  |  |  |  | software
2025-07-09 | 9:00 | 16:30 | 7:30 | Setting up and storing alarms | Made mode controller task |  |  |  | software
2025-07-10 | 9:30 | 12:00 | 2:30 | Implementing ui for pill alarms | Started mp3 player implementation |  |  |  | software
2025-07-11 | 9:30 | 13:00 | 3:30 | Discovered mp3 player is broken (solve later) | Started button implementation |  |  |  | hardware
2025-07-14 | 10:00 | 16:30 | 6:30 | Setting up i2c protocol | Implemented button display controll | made button configuration tasks |  |  | software
2025-07-15 | 9:30 | 18:00 | 8:30 | Designed flowchart for pill alarm | Implemented state machine for pill alarm | Started implementing state machine sleep alarm. |  |  | software
2025-07-16 | 9:30 | 11:00 | 1:30 | Finished sleep alarm state machine |  |  |  |  | software
2025-07-17 | 10:30 | 16:00 | 5:30 | Started implementing voicetrainer function |  |  |  |  | software
2025-08-25 | 11:00 | 15:30 | 4:30 | implemented collecting audio | implemented fft | stated implementing vocal feedback |  |  | software
2025-08-26 | 10:30 | 15:00 | 4:30 | Implemented Voicetrainer UI |  |  |  |  | software
2025-10-03 | 9:00 | 12:00 | 3:00 | Designed basic components in solid edge |  |  |  |  | case
2025-10-09 | 17:00 | 20:00 | 3:00 | Started designing new case |  |  |  |  | case
2025-10-10 | 9:30 | 12:00 | 2:30 | Made new component lis and ordered components |  |  |  |  | case
2025-11-01 | 12:30 | 16:00 | 3:30 | Redesigned buttons |  |  |  |  | case
2025-11-02 | 10:00 | 20:00 | 10:00 | Designing case (PCB layer) |  |  |  |  | case
2025-12-18 | 10:00 | 18:00 | 8:00 | Designing case (button layer) | Ordering more components |  |  |  | case
2025-12-19 | 10:00 | 16:00 | 6:00 | disigning case (display layer |  |  |  |  | case
2025-12-23 | 10:00 | 16:00 | 6:00 | Printed and redesigned and reprinted button layer |  |  |  |  | case
2025-12-24 | 10:00 | 16:00 | 6:00 | Printing top layer | Designing last components and fixing mistakes | gamma/ preparing assambly/ checking model (finished?) |  |  | case
2025-12-30 | 10:00 | 16:00 | 6:00 | Printing top case (again) | testing old hardware | Trying to fix main display |  |  | hardware
2025-12-31 | 10:00 | 16:00 | 6:00 | Fixed main display (finaly) | printing bottom case |  |  |  | hardware
2025-01-01 | 15:00 | 19:00 | 4:00 | troubleshooting main display (again)(fixed) | Started assembly |  |  |  | hardware
2025-01-02 | 10:00 | 18:00 | 8:00 | Contineud assambly and rewiring | Display stopped working again. (i dont know why |  |  |  | hardware
2025-01-03 | 12:00 | 16:00 | 4:00 | trying to fix display (no succes) |  |  |  |  | software
2025-01-04 | 11:00 | 20:30 | 9:30 | Power supply Broke (fixed it) | Fixed main display (GPIO11 broken) | Added software & hardware for mp3 | Finished assembly | Added summer/winter time | hardware
|  | total: | 170:00